## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 | Milestone 1 | US-01 | As a Developer, I want to paste Python code into the tool so the system can accept it for parsing and analysis. | MUST HAVE | — | DADISETTY AAKANKSHA | 3- Completed
Milestone 1 | Milestone 1 | US-02 | As a Developer, I want the code parsed using Python's AST so that structural elements like functions, variables and imports are extracted. | MUST HAVE | US-01 | DADISETTY AAKANKSHA | 3- Completed
Milestone 1 | Milestone 1 | US-03 | As a Developer, I want a NodeVisitor to traverse the AST so that I can collect details about all code elements. | MUST HAVE | US-02 | DADISETTY AAKANKSHA | 3- Completed
Milestone 2 | Milestone 2 | US-04 | As a Developer, I want syntax errors detected automatically so that the user knows exactly which line has a problem. | MUST HAVE | US-03 | DADISETTY AAKANKSHA | 3- Completed
Milestone 2 | Milestone 2 | US-05 | As a Developer, I want unused imports, bare except clauses, and dangerous functions (eval/exec) flagged so the code is safe and clean. | MUST HAVE | US-04 | DADISETTY AAKANKSHA | 3- Completed
Milestone 2 | Milestone 2 | US-06 | As a Developer, I want the Groq LLaMA AI to review my code and return suggestions, security issues and optimizations in JSON format. | MUST HAVE | US-05 | DADISETTY AAKANKSHA | 3- Completed
Milestone 3 | Milestone 3 | US-07 | As a Developer, I want a Reflex web app with a sidebar and 5 navigation tabs so I can interact with all features through a browser. | MUST HAVE | US-06 | DADISETTY AAKANKSHA | 3- Completed
Milestone 3 | Milestone 3 | US-08 | As a Developer, I want an Analysis Report tab showing quality score (0-100), grade (A-F), and issue list so I can review results clearly. | MUST HAVE | US-07 | DADISETTY AAKANKSHA | 3- Completed
Milestone 3 | Milestone 3 | US-09 | As a Developer, I want a Security Audit tab that isolates all critical and error-level issues so I can focus on fixing security problems. | SHOULD HAVE | US-08 | DADISETTY AAKANKSHA | 3- Completed
Milestone 4 | Milestone 4 | US-10 | As a Developer, I want an AI chat assistant so I can ask questions about my code and get context-aware responses from the AI. | SHOULD HAVE | US-09 | DADISETTY AAKANKSHA | 3- Completed
Milestone 4 | Milestone 4 | US-11 | As a Developer, I want an analysis history tab so I can track my past code quality scores and see improvement over time. | SHOULD HAVE | US-10 | DADISETTY AAKANKSHA | 3- Completed
Milestone 4 | Milestone 4 | US-12 | As a Developer, I want the app deployed on Reflex Cloud so my mentor can access and evaluate it from any browser. | MUST HAVE | US-11 | DADISETTY AAKANKSHA | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M1 BACKLOG
US-01 | T-01 | Analyze project requirements and plan code parsing module | 2025-12-01 | 2025-12-02 | [Your Name] | Design | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Set up project folder structure and install dependencies | 2025-12-02 | 2025-12-03 | [Your Name] | Setup | 3- Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Implement code_visitor.py using AST NodeVisitor | 2025-12-03 | 2025-12-05 | [Your Name] | Build | 3- Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-04 | Implement code_parser.py – parse code, extract metrics | 2025-12-05 | 2025-12-07 | [Your Name] | Build | 3- Completed | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M2 BACKLOG
US-04 | T-05 | Implement error_detector.py – all 7 static checks | 2025-12-08 | 2025-12-10 | [Your Name] | Build | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-05 | T-06 | Build quality scoring algorithm (0-100) and grade (A-F) | 2025-12-10 | 2025-12-11 | [Your Name] | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
US-06 | T-07 | Implement ai_suggestor.py – connect Groq LLaMA via LangChain | 2025-12-11 | 2025-12-13 | [Your Name] | Build | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US-06 | T-08 | Fix langchain import error (langchain_core.messages) | 2025-12-13 | 2025-12-13 | [Your Name] | Fix | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
M3 BACKLOG
US-07 | T-09 | Build Reflex app skeleton – rxconfig, sidebar, 5 tabs | 2025-12-15 | 2025-12-16 | [Your Name] | Build | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-10 | Fix rxconfig app_name mismatch error | 2025-12-16 | 2025-12-16 | [Your Name] | Fix | 3- Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-11 | Build Analysis Report tab – score cards, issue list, AI display | 2025-12-17 | 2025-12-19 | [Your Name] | Build | 3- Completed | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-12 | Fix UntypedVarError – replace List[Dict] with rx.Base classes | 2025-12-19 | 2025-12-19 | [Your Name] | Fix | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-13 | Build Security Audit tab | 2025-12-20 | 2025-12-20 | [Your Name] | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M4 BACKLOG
US-10 | T-14 | Build AI Assistant chat tab with send_chat async handler | 2025-12-22 | 2025-12-23 | [Your Name] | Build | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-15 | Fix websocket error – add yield after state changes | 2025-12-23 | 2025-12-23 | [Your Name] | Fix | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-11 | T-16 | Build History tab with HistoryEntry typed class | 2025-12-24 | 2025-12-24 | [Your Name] | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
US-12 | T-17 | Deploy app using reflex deploy, update rxconfig api_url | 2025-12-25 | 2025-12-26 | [Your Name] | Deploy | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0
US-12 | T-18 | Add GROQ_API_KEY to Reflex Cloud Secrets and redeploy | 2025-12-26 | 2025-12-26 | [Your Name] | Deploy | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Milestone 1 | Day 1 | No impediments | Analyzed project requirements and planned module structure for AI Code Reviewer
Milestone 1 | Day 2 | Difficulty understanding AST NodeVisitor pattern | Studied Python AST documentation and tested simple code traversal examples
Milestone 1 | Day 3 | Handling edge cases in code_visitor.py for complex nested functions | Implemented and tested CodeVisitor class with multiple Python code samples
Milestone 1 | Day 4 | code_parser.py metrics not counting blank vs comment lines correctly | Fixed line counting logic and validated against multiple test files
Milestone 1 | Day 5 | No impediments | Completed Milestone 1 – code_parser.py and code_visitor.py fully working
Milestone 2 | Day 1 | Unsure which static checks to implement in error_detector.py | Reviewed common Python linting rules and implemented 7 key checks
Milestone 2 | Day 2 | eval/exec detection returning false positives | Refined AST call detection logic to check only direct Name node calls
Milestone 2 | Day 3 | Groq API returning unstructured text instead of JSON | Updated system prompt to strictly enforce JSON-only response format
Milestone 2 | Day 4 | langchain.schema import not found (deprecated in newer LangChain) | Changed import to langchain_core.messages – resolved immediately
Milestone 2 | Day 5 | No impediments | Completed Milestone 2 – error_detector.py and ai_suggestor.py working
Milestone 3 | Day 1 | rxconfig.py app_name did not match folder name – ModuleNotFoundError | Fixed app_name in rxconfig.py to match ai_code_reviewer folder name
Milestone 3 | Day 2 | Reflex foreach throwing UntypedVarError for List[Dict] state | Replaced all List[Dict] with typed rx.Base classes (Issue, ChatMessage)
Milestone 3 | Day 3 | Analysis Report tab not rendering score cards correctly | Debugged Reflex state binding and fixed metric_card component layout
Milestone 3 | Day 4 | Security Audit tab showing all issues instead of only errors | Added severity filter in foreach to show only error-level issues
Milestone 3 | Day 5 | No impediments | Completed Milestone 3 – all 5 tabs working in Reflex app
Milestone 4 | Day 1 | AI chat assistant causing websocket disconnect error | Added yield after each state change in async send_chat handler
Milestone 4 | Day 2 | History tab not updating after new analysis | Fixed HistoryEntry typed class and history.insert() in run_analysis
Milestone 4 | Day 3 | reflex deploy failing – missing libraries in requirements.txt | Added langchain-core, python-dotenv to requirements.txt and redeployed
Milestone 4 | Day 4 | Deployed app backend not connecting to frontend | Updated api_url in rxconfig.py with deployed backend URL and redeployed
Milestone 4 | Day 5 | GROQ_API_KEY not available in cloud environment | Added GROQ_API_KEY to Reflex Cloud Secrets dashboard and redeployed

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Milestone 1 | 2025-12-01 | 2025-12-07 | [Your Name] | Write unit tests for each module before moving to next | Skipping documentation while coding | Daily code review and testing | Created test cases for code_parser and code_visitor modules
2 | Milestone 2 | 2025-12-08 | 2025-12-14 | [Your Name] | Check library changelogs before upgrading dependencies | Using deprecated APIs without checking docs first | Modular file structure – one responsibility per file | Fixed langchain import; now always verify imports against current docs
3 | Milestone 3 | 2025-12-15 | 2025-12-21 | [Your Name] | Read Reflex documentation before implementing state features | Using plain Python types in Reflex state (use rx.Base instead) | Testing each UI tab separately before integration | Replaced all List[Dict] with typed rx.Base classes; app runs cleanly
4 | Milestone 4 | 2025-12-22 | 2025-12-28 | [Your Name] | Add all libraries to requirements.txt from the start of the project | Testing only locally without thinking about cloud deployment | Using yield in all async Reflex handlers | Successfully deployed on Reflex Cloud with working AI backend