## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Milestone | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | DADISETTY AAKANKSHA | 2026-02-15 | ModuleNotFoundError: app_name in rxconfig.py did not match the folder name 'ai_code_reviewer' | Milestone 1 | Self | Logical | Updated app_name in rxconfig.py from 'app' to 'ai_code_reviewer' to match folder name | 2026-02-16 | Closed | Resolved immediately after checking Reflex documentation
2 | DADISETTY AAKANKSHA | 2026-03-07 | ModuleNotFoundError: No module named 'langchain.schema' – import was deprecated in newer LangChain versions | Milestone 2 | Self | Standards | Changed import from langchain.schema to langchain_core.messages for HumanMessage and SystemMessage | 2026-03-11 | Closed | langchain_core.messages is the correct import in LangChain v0.2+
3 | DADISETTY AAKANKSHA | 2026-03-17 | UntypedVarError: Reflex foreach could not iterate over State.issues of type List[Dict] | Milestone 3 | Self | Logical | Replaced all List[Dict] state variables with typed rx.Base classes: Issue, ChatMessage, HistoryEntry | 2026-03-17 | Closed | Reflex requires typed rx.Base subclasses for foreach iteration
4 | DADISETTY AAKANKSHA | 2026-03-26 | Websocket disconnect error when AI chat assistant send_chat function was called | Milestone 4 | Self | Logical | Added yield after appending user message and after appending AI reply in async send_chat handler | 2026-03-29 | Closed | Reflex async handlers must yield after each state mutation to push updates to browser
5 | DADISETTY AAKANKSHA | 2026-03-27 | Unused imports in error_detector.py were flagging standard library modules incorrectly as unused | Milestone 2 | Self | Logical | Fixed AST Name traversal to also capture attribute accesses (e.g., os.path) in used_names set | 2026-03-30 | Closed | Updated _check_unused_imports to include Attribute node value names
6 | DADISETTY AAKANKSHA | 2026-03-28 | reflex deploy failed with dependency error – langchain-core and python-dotenv missing from requirements.txt | Milestone 4 | Self | Standards | Added all missing packages (langchain-core, python-dotenv, langchain-groq) to requirements.txt | 2026-03-31 | Closed | Always list all installed packages in requirements.txt before deployment
7 | DADISETTY AAKANKSHA | 2026-03-29 | Deployed app frontend loaded but AI features returned no response – backend not connecting to frontend | Milestone 4 | Self | Logical | Updated api_url in rxconfig.py with the actual deployed backend URL and ran reflex deploy again | 2026-04-01 | Closed | Two-step deployment required: first deploy to get URL, then update rxconfig and redeploy
8 | DADISETTY AAKANKSHA | 2026-03-30 | GROQ_API_KEY not found in cloud environment – AI suggestions returning 'API key missing' message | Milestone 4 | Self | Others | Added GROQ_API_KEY as a secret in Reflex Cloud dashboard under Project Settings > Secrets | 2026-04-01 | Closed | Environment variables must be set as Secrets in Reflex Cloud, not just in local .env file

## Sheet2
Logical
User Interface
Maintainability
Standards
Others